Annexure C

Confidential     				Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to JSACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Mr. Tara kanta Gopal | 91-7250762306 |
| Prof. Laxmidhar Swain | 91-9438470853 |
| Officials from JSACS(as facilitator) | Dr. Sami Akhter, MEO, JSACS. |

| Name of the NGO: | Manthan, Dhanbad |
| --- | --- |
| Typology of the target population: | MSM – 500 Targets. |
| Total population being covered against target | 524 MSMs - in 10 hotspots. Goti 368, Panti-83, Double decker 68 & TG-5. |
| Dates of Visit: | February 25-27, 2016 |
| Place of Visit: | - Dhanbad Rly station, 2. Bhuli More, 3.Bank More, 4. Jharia children’s park, 5. Community Swasthaya Kendra (ICTC), Chasnala, 6. At Dhanbad, OSD, OST Centre, ICTC, ART & PPTCT centres. |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor |  |
| 41%-60% | C | Average |  |
| 61%-80% | B | Good | Recommended for continuation |
| >80% | A | Very Good | Recommended for Renewal during the year 2016 and Beyond with specific focus for developing learning sites as best practices. |

Specific Recommendations;

- Payments to the project need to be released from JSACS in time not to hamper the work. - Found the TI project experiences difficulty in targeting TI services for MSMs. Based on the findings, a fresh proposal need to be developed for targeting individual MSMs are being targeted. - JSACS to Conduct Training & Refresher in time in the implementation year. - Peer Educators intensive training needed to be conducted. - “Adhikar”–the MSM Organisation need to be strengthen by exploring linkage with other resource agencies. Date of Report Submission: 3 March 2016.

Name of the evaluators        					Signature

| Mr. Tara, External Evaluator |  |
| --- | --- |
| Prof. Laxmidhar Swain, Team Leader |  |