Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

Background of Project and Organization:

The organization started working since 2004.It is Ranchi based organization and the focus of the organization is on health, education, HIV/AIDS awareness, women empowerment and targeted interventions. The donor of the organization is CRY since 2004 working five block in Hazaribagh district. The Organization started working with JSACS since 2010.

Name and address of the Organization: Sankalp Jyoti

New Colony, Tungri

Dist – Chaibasa

West Singhbhum

Mob: 8051177067 (PM)

: 7301109840

Email: sankaljyoti@hotmail.com

Sanjeev Kumar 9431178150

Year and month of project initiation:September’ 2010

Evaluation team

-   S.N.Ghosh(Team Leader)

-   Nanhelal Sharma (External Evaluator)

-Jyoti Kumar (Finance Auditor)

-   Md.Masoom Ali  (JSACS Official)

Time frame: 25th Feb’14 to 27th Feb’16

Profile of TI

(Information to be captured)

- Target Population Profile:FSW

- Targeted population :500

- Type of Project: Core population

- Sub group : Street, Home, slum and Lodge based

- Target Area : Jantugara,Maluka,Lupungutu,Jaintgarh,Narsanda,CKP,Sasanpata,Pancho

- Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc…

Mr. Mukesh project director of the organization participated in the staff recruitment process, project planning, and review meetings.Mr.Mukeshthe project director is providing his inputs in preparing in the monthly review meetings.The project manager is responsible for overall implementation of the project.

II. Organizational Capacity

- Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover.

All staff as approved in the proposal was appointed. The staff retention is good..There was no staff from the HRG community. PE to HRGs ratio is 1:60.More thanPEs belong age group of above 30.The ORW to HRGs ratio is 1:250.The Project Management Committee does not exist.The project Director attended monthly meetings but it less than 80%.He provides his support and guidance in program planning and supervision.

2. Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

More than 80% of the staff and Peer Educators had attended the trainings organized bySTRC.Trainingregister was available but without detailed minutes. Staff and peers need more training in micro planning and outreach planning, reporting, data management and budget utilization. The staff got trainings from project Pehchan also.

- Infrastructure of the organization :The organization has rented building .Assets like Furniture, Iron Chairs-3,Cushion Chair-2,plastic chair-10,Tv-1,DVD-1,Printer-1,Almirah-1,CPU with Monitor-1,Table-5,C table-1,Fan-2

- Computer, Almirah, DVD playerChair,Stabilizer, File rack, Table, and TV are available in theproject office.Local purchasing also included in the asset register.

4. Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

Form A (Site code missing) did not have complete information (movement details).  Line listing available in soft & hard copy. 551, in the line register the PM was unable to explain the first and second Meet,(PM unable to explainReferral slips, clinical registers not well maintained. Micro plan was not updated periodically and not in use for implementation.

III. Program Deliverables

Outreach

1. Line listing of the HRG by category.

Total 500

All HRGs are Street based.

2. Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling.

NA

3. Registration of truckers from 2 service sources i.e. STI clinics and counseling.

NA

4. Micro planning in place and the same is reflected in Quality and documentation.

Micro Planning is in place and updated. Understanding of themicro planning is not clear among staff and peers

5. Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

Target population is500 and street based.

6. Outreach planning – quality, documentation and reflection in implementation

Outreach planning, monthly review meetings conducted but not properly followed..

7. PE: HRG ratio, FSW

Ratio of peer educator and HRGs is 1: 60

5. Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members

The TI maintains regular contacts. HRGs were contacted by the PEs minimum twice in a month; provide condom, PT, ICTC, RMC, ART,Syphilis, and social marketing services.

9. Documentation of the peer education

Peer educators arenot maintaining form B but use daily dairy.But daily dairy was not well maintained

10. Quality of peer education- messages, skills and reflection in the community

All Peer educators are trained & message dissemination is notsatisfying. Interaction of peerswith community is good but poor knowledge of peers produced ineffective impact in the field.

11. Supervision- mechanism, process, follow-up in action taken etc

Mechanism is there but PM is weak in monitoring. One of the ORW is beyond control of PM.

IV. Services

1. Availability of STI services – mode of delivery, adequacy to the needs of the community.

4PPP doctors are in place and three are trainedand one untrained,but the knowledge level of Syndromic management is poor. Presently,STI Kits Notavailable March 2013- 7th August, 2015. The PPP doctor met in thefield did not understand the abbreviation of PE and HRG.He is unclear about partner’s notification.

2. Quality of the services- Infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

Location--The clinic setup is good and it is in the field area.STI drugs are presently available (Kit-1, 2,4,6,7 available). Privacy isnot properly maintained.

3. In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

NA

4. Quality of treatment in the service provisioning- adherence to syndromes treatment protocol, follow up mechanism and adherence, referrals to ICTC,ART, DOTS centre and Community care centers.

Not properly maintaining the Syndromic management protocol. Referrals of ICTC and ART.The coordination is good.

5. Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

All documents are there but understanding is poor and not using properly. There was no referral slips for STI clinics.

6. Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

More than 90 % distribution of condoms observed.They get the condoms from SACS. Condoms are distributed through ORWs,PEs and Outlets (Betel Shop), human outlets

7. No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

Condom is available in hot spots & social marketing of condom is seen. Human outlets distribute free condoms.

8. No. of Needles / Syringes distributed through outreach / DIC.

NA

9. Information on linkages for ICTC, DOT, ART, STI clinics.

Information on linkages with ICTC, STI & ART is good. Linkage with DOTS isnil in two years

10. Referrals and follows up

Referrals only for ICTC, ART,DOTS&PPP happen. But referral slip is not maintained.

V. Community participation

1. Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

Not any initiation on group formation.

2. Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

Poor community participation. No proper documentation on the same.The community is unaware about all the services of TI

VI. Linkages

1. Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

Linkages have been established with ICTC& ART only. Poor coordination was observed for DOTS.Referral .

2. Percentages of HRGs tested in ICTC and gap between referred and tested.

Referral 1833 & tested : 1029

3. Support system developed with various stakeholders and involvement of various stakeholders in the project.

No stakeholders meet was organized in two years.

VIIFinancial systems and procedures

- Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems Endorsed by SACS/NACO- supporting official communication.

NGO-CBO guidelines adhered / approved systems endorsed by SACS/NACO followed. Single account with joint signatories.

- Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of  using printed and serialized vouchers, approval systems and normsverification of documents with minutes, quotations, bills, vouchers, stock and issue registers practice of  settling of advances before making further payments

All payment systems as per SACS guideline. The TI using printed vouchers and approval system.

Cash book properly maintained.

- Systems of  procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking Procurementfollowed by norms.

- Systems of documentation- Availability of bank accounts (maintained jointly, reconciliation made monthly basis), audit reports.

Separate Saving Bank account opened by the organization for the project and jointly

Operated.

VIII. Competency of the project staff

VIII a. Project Manager

Educational qualification & Experience as per norm, knowledge about the proposal, Quarterly and monthly plan in place, financial management, computerization and management of data, knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, mentoring and field visit & advocacy initiatives etc.

The Project Manager is there in the project for more than 3years. Hegot trainings three times. He is bachelor in Ayurvedicmedicine,Preventive and promotive health care,fellowship in clinical research (APPOLLO,Hyd),MSW.His knowledge and skill in planning, understanding on various formats, supervision, using computer and data management is poor. Project Manager needs more handholding support to manage the program activities and data management.

VIII b. ANM/Counselor

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

The position of counselor is filled and she got the trainings from other project.

VIII c. ANM/Counselor in IDU TI

Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers. Working knowledge about local drug abuse scenario, drug-related counseling techniques (MET RP, etc.), drug-related laws and drug abuse treatments.

For ANM, adequate abscess management skills. NA

VIII d. ORW

Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

Two ORWs are there and they attended trainings organized by STRC. Their knowledge and understanding on basics of HIVAIDS, STI, and various formats was notall satisfying. They also need hand holding.

VIII e. Peer educators

Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

8PEswere working .6 peers are above 30. Knowledge on basics of HIV/AIDS and condom demo was unsatisfyingTheir knowledgein prioritization, micro plan and outreach planning equally bad.

VIII f. Peer educators in IDU TI

Prioritization of hotspots, condom demonstration, importance of RMC and ICTC testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

NA

VIII g. Peer Educators in Migrant Projects

Whether the Peers represent the source States from where maximum migrants of the area belong to, whether they are able to priorities the networks/locations where migrants work/reside/access high risk activities, whether the peers are able demonstrate condoms, able to plan their outreach, able to manage the DICs/ health camps, working knowledge about symptoms of STI, issues related to treatment of TB, services in ICTC & ART.

NA

VIII h. Peer Educators in Truckers Project

Whether the peers represent ex-truckers, active truckers, representing other important stake holders, the knowledge about STI, HIV, and ART. Condom demonstration skills, able to plan their outreach along with mid-media activity, STI clinics.

NA

VIII  M&E officer

Whether the M&E officer ( FSW and MSM/TG TIs with more than 800 population and all migrant TIs are eligible for separate M&E officer) is able to provide analytical information about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.

M&E and Accountant is working and attended trainings organized by STRC.He needs clarity on programme activities, budget utilization and monitoring.

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

Micro plan and outreach plan was available. However, staff clarity on these tools and process was unclear. A broad monthly planning was made for program implementation based on the review. Micro plan not updated properly

IX. b. Outreach activity in Truckers and Migrant Project

Interact with all PEs and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in service uptake that is whether enough clinic footfalls, Counseling is happening.

Whether the stake holders are aware of the outreach sessions. Whether the timings of the outreach sessions are convenient / appropriate for the truckers/migrants when they can be approached etc.

NA

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

Atleast80% of the community members attending FGD were not convinced with the services. The DIC is located far off from their residence.

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

The CMC is formed at the project and field level but not vibrant.Other committees do not exist.

XII. Commodities

Hotspot / project level planning for condoms, needles and syringes. Method of demand calculation, Female condom programme if any,

Condom demand analysis is not properly done. However, supply of condom is made based on the requirement. Free condom supply was in place. Social marketing was initiated, During the physical verification the stock was found mismatched

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

No stakeholders meet was organized in two years. Staff knowledge on planning and implementation of advocacy activity needs to be improved

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.No work on social protection schemes.

XV. Best Practices if any

No best practices observed