Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

ORGANIZATION PROFILE

Tata Steel Rural Development Society

# Tata Steel Corporate Sustainability Services (CSS) works in social development through three corporate NGOs namely Tata Steel Rural Development Society, Tribal Cultural Society, Tata Steel Family Initiatives Foundation and the Urban Services Department. Health initiatives are provided through 32 general health, maternal and child health care clinics that cater to both rural and urban population in and around Jamshedpur. These clinics also provide services for sexually transmitted infections where high risk cases get screened and treated.

# TSRDS was established in 1979 and registered under the Society Registration Act 21, 1860 and has a special focus on sustainable livelihood, health and hygiene, empowerment and environment in the rural areas. It started with 32 villages and now covers over 800 villages in Jharkhand, Orissa and Chattisgarh. TSRDS is working on approx. 20 projects at present funded by various funders and government. TSRDS has a Mission of creating favorable social environment to enable business Its Objective is to improve the economic and social status of the community.

# TSRDS also has a well organized procurement system and accounts department to procure the goods needed and for the maintenance of the accounts.

# TSRDS has an experience of 15 years in working with long distance truck drivers and helpers for the prevention of STI/HIV/AIDS in collaboration with Transport Corporation of India Foundation (TCIF) under “Kavach” project. It has the trained manpower and established infrastructure to implement the project efficiently. Under the project, one static “Khushi Clinic” is run at Transport Parking, Dimna and five satellite “Khushi Clinics” are run at five major halt points in Jamshedpur. These two clinics are managed by a highly trained clinical team comprising of a doctor, counselor and a clinic attendant. In turn these clinical teams are managed by qualified and skilled professionals and higher management who provide continuous guidance and innovative ideas to improve the service delivery system as well as to reach out to the maximum affected target population.

o   Chief Functionary: Mrs.SANJUKTA , Project Director

o   Evaluation team:

SUBHARTHI MUKHERJEE, ( External Evaluator & Team Leader )

RAMESH KUMAR , ( External Evaluator )

ABHISHAK ( Finance )

Mr.SIDDHATHA GOSWAMI (Jsacs)

o   Time frame 22th ,23th, 24th February 2016

Profile of TI

(Information to be captured)

o   Target Population Profile	: TRUCKERS

- Size of Target Group(s) As per JSACS from January onwards is 20000.

Clinic		Total Coverage 				 G. Total	Total	covrage	Total	Total		Event

A	B	C	D	B TO D (F)		A& F

Month	Footfall	IPC	IPC Cov	Street Play 	A/V Show	Health Games	BCC	Counselling		ICTC Refer	ICTC Test	STI	Health Camp

April	1207	126	1500	0	379	2445	2824	201	4324	148	33	128	1

May 	1135	121	1464	0	376	2420	2796	241	4260	205	6	147	1

Jun	1438	114	1352	0	419	3090	3509	183	4861	170	20	154	1

July	1547	133	1625	0	448	2995	3443	220	5068	218	47	201	1

Aug	1451	129	1550	218	304	2582	3104	216	4654	192	157	182	1

Sep	2035	115	1445	258	456	3107	3821	258	5266	250	125	215	2

Oct	1955	196	2569	217	153	2933	3303	236	5872	199	131	184	2

Nov	2178	254	3257	0	232	3005	3237	245	6494	217	150	205	4

Dec 	2264	132	1607	217	225	2898	3340	220	4947	210	182	175	2

Jan	1954	150	1881	0	207	2600	2807	238	4688	221	156	213	3

Feb							0		0

Mar							0		0

Total	17164		18250	910	3199	28075		2258	50434	2030	1007	1804	18

TARGET	20000								80000		2000	2000

Rest -target 	2836										993	196

Total AWARNESS TARGET Clinic footfall x 4 (20000 x4=80000)

Data add-Static Clinic and Extension Clinic (JTN Dimna,Burmamains Truck Park,Burmamains Durga Puja Maidan

o   Target Area, Dist. EAST SINGBHUM , Jharkhand

Key Findings and recommendations on Various Project Components

I. Organizational support to the program

Interaction with key office bearers support to the community, initiation of advocacy activities, monitoring the project etc…

Evaluators were able to meet the Project Director ,  Project  Manager , Counselor , Accountant , 4ORW’ but ONE POST is vacant last one year and 10 peer educators. The appointment letter in the separate personal file for each staff. Photo-ID cards were given to the staffs for ease during work. Following is the staff details. The entire project managed by the Project manager with the support of the PD as well as the Governing Body. The project Manager concentrated more over on transparency in the project. The thought which gives conceptual clarity and decentralized system of the organization. The periodical visits and discussion by the Project Director gives much direction to the project as well to the staff. Since organization is having different projects the linkages facility also available in the project which caters the community need too.

II. Organizational Capacity

- Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, 	role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover

The project team comprises of  Project Director, Project Manager, Counselor, Accountant, 03 ORWs , 10 PEER Educators.  All the staff present during the discussion at office on the 1st day. The staff turnover is less in the project. Most of the staffs are experienced. There is a team work reflects in the project. The appointment letter and roles & responsibilities are given and maintained individual personal files.

| S.N | NAME | Sex | DESGINATION | Contact No | Age | Qualification |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Sanjukta Nayak | F | Project Director | 9204058301 | 59 | MSc, (Physics) |
| 2 | KRISHAN DAYAL. GOSWAMI | M | PROJECT CO-ORDINATOR | Left (1st May 2015) | 40 | MSW |
| 3 | DR.SANTOSH GUPTA | M | DOCTOR | 7209406765 | 40 | MBBS |
| 4 | SANTOSH KUMAR | M | COUNSELORE | 9031582630 | 39 | MA(Sociology) |
| 5 | BIBHUTI ALKISHOR | M | HEALTH EDUCATOR | 7209628029 | 55 | IA |
| 6 | UJJWALA TOPNO | F | HEALTH EDUCATOR | 8809909448 | 38 | MSW |
| 7 | PARSISH MARANDI | F | HEALTH EDUCATOR | Left(1st Mar 2015) | 40 | BA |
| 8 | JUNIKA Nag | F | HEALTH EDUCATOR Cum Clinic attendant | 9234275271 | 47 | IA |

| Sl No | NAME | Sex | Age | Poject joining year | Qualification |
| --- | --- | --- | --- | --- | --- |
| 1 | Mokhtar Ray | M | 50 | 2006 | 7th |
| 2 | Jaiprakash RAI | M | 30 | 2008 | BA |
| 3 | Devendera Prasad | M | 48 | 2006 | B Com |
| 4 | Birendra kumar | M | 40 | 2011 | Plus II |
| 5 | Niranjan kumar | M | 26 | 2012 | BA |
| 6 | Ganesh Chandra | M | 28 | 2012 | Matric |
| 7 | Ajay kumar | M | 45 | 2012 | Matric |
| 8 | Ranjit kumar | M | 32 | 2011 | Plus II |
| 9 | Manish kumar | M | 24 | 2012 | Matric |
| 10 | Shiv Prakash | M | 27 | 2012 | Plus II |

3.  Infrastructure of the organization

The project office cum DIC is centrally located but for some field not easily accessible to the community members for the distance. The space is sufficient for having the routine office work and for group meetings. But the DIC space need to modify. The basic infrastructure and the computer with printer are available in the office.

4.  Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of 
	documents, mechanism of review and action taken if any, timeliness of reporting and feedback 
	mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

The reporting is as per the JSACS / NACO protocol/guidelines. CMIS prepared periodically. The monthly planning is done by the ORWs and PM during the monthly review meeting.

The the peer educators plan as per the dues and analysis report. As such out reach and micro plan was upgraded periodically. Which is the indicator for effective outreach and provide the service delivery of the project to the community. And this will be need based service practice. So that systematic approach and monitoring of the individual seen. Also observed and seen the documentation on condom usage is individual tracking is also maintained. The condom gap Analysis for TI’s is maintained in the project by the ORW.

Because of the active  and enthusiastic staff the project documentation in place. Weekly and monthly review meeting is taking place as per the registers. The other registers like Community event reg. , Purchase committee reg., Staff selection committee .

The reports were verified by the PM, but not seen any constructive suggestions. Meeting registers and minutes are maintained and need qualitative narration. If the technical support available to the project staff for documentation than it will be model project or consider as the learning site.

III. Program Deliverables Outreach

- Line listing of the HRG by category.

Line listing of HRGs done and maintained a soft copy with unique ID number. The master register maintained  and the target from JSACS is June 2015onwards is 20000 but  service provided 17164. During the project assessment period the PE’s contacted all the HRG’s in the hotspots

|  |  |  |  | Truckers Intervention Project Data -April 15 to March 2016 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Clinic |  | Total Coverage |  |  |  | G. Total | Total | covrage | Total | Total |  | Event |
|  |  |  | A | B | C | D | B TO D (F) |  | A& F |  |  |  |  |
| Month | Footfall | IPC | IPC Cov | Street Play | A/V Show | Health Games | BCC | Counselling |  | ICTC Refer | ICTC Test | STI | Health Camp |
| April | 1207 | 126 | 1500 | 0 | 379 | 2445 | 2824 | 201 | 4324 | 148 | 33 | 128 | 1 |
| May | 1135 | 121 | 1464 | 0 | 376 | 2420 | 2796 | 241 | 4260 | 205 | 6 | 147 | 1 |
| Jun | 1438 | 114 | 1352 | 0 | 419 | 3090 | 3509 | 183 | 4861 | 170 | 20 | 154 | 1 |
| July | 1547 | 133 | 1625 | 0 | 448 | 2995 | 3443 | 220 | 5068 | 218 | 47 | 201 | 1 |
| Aug | 1451 | 129 | 1550 | 218 | 304 | 2582 | 3104 | 216 | 4654 | 192 | 157 | 182 | 1 |
| Sep | 2035 | 115 | 1445 | 258 | 456 | 3107 | 3821 | 258 | 5266 | 250 | 125 | 215 | 2 |
| Oct | 1955 | 196 | 2569 | 217 | 153 | 2933 | 3303 | 236 | 5872 | 199 | 131 | 184 | 2 |
| Nov | 2178 | 254 | 3257 | 0 | 232 | 3005 | 3237 | 245 | 6494 | 217 | 150 | 205 | 4 |
| Dec | 2264 | 132 | 1607 | 217 | 225 | 2898 | 3340 | 220 | 4947 | 210 | 182 | 175 | 2 |
| Jan | 1954 | 150 | 1881 | 0 | 207 | 2600 | 2807 | 238 | 4688 | 221 | 156 | 213 | 3 |
| Feb |  |  |  |  |  |  | 0 |  | 0 |  |  |  |  |
| Mar |  |  |  |  |  |  | 0 |  | 0 |  |  |  |  |
| Total | 17164 |  | 18250 | 910 | 3199 | 28075 |  | 2258 | 50434 | 2030 | 1007 | 1804 | 18 |
| TARGET | 20000 |  |  |  |  |  |  |  | 80000 |  | 2000 | 2000 |  |
| Rest -target | 2836 |  |  |  |  |  |  |  |  |  | 993 | 196 |  |
|  |  |  | Total AWARNESS TARGET Clinic footfall x 4 (20000 x4=80000) |  |  |  |  |  |  |  |  |  |  |

- Micro planning in place and the same is reflected in Quality and documentation.

The proper micro planning is not done at project level. The ORWs assigning the work to the peer educators during the weekly meeting and the same is carried out by the peer educator The project team as whole is not perceived the importance of micro planning.  The community members are collecting the commodities as per their requirements. The condom gap analysis which is done is not in qualitative documentation.

Contact Mapping 1

Contact Mapping 2

Line Listing

Hot Spot load Mapping

Condom Availability & Accessibility Mapping

Spot Analysis

Seasonality Map

Opportunity Gap Analysis

Condom Gap Analysis & usage percentage

- Outreach planning - quality, documentation and reflection in implementation

Out reach plan based upon the typology and volume .The Out reach planning is micro plan condom gap analysis volume wise plan , hotspot analysis  prepared and updated & used for the outreach. The same plan is used by the ORW and during the weekly & monthly meeting is revised. Based upon that the plan was prepared. The volume based categorization, condom demand and gap, gaps in STI / ICTC etc are to be documented and plan activities accordingly.

4.  PE: HRG ratio: 1 :200.

6.Documentation, of the peer education

The peer diaries are maintained by the literate peers. Condom Gap Analysis , Social , Hotspot analysis, Service Map available but need to be updated.  The ORWs support for the peer educators in documenting , referral system and in the field level observed during the field visits. The form B is incomplete and the team should take up the matter seriously as it is essential for planning..

7.Quality and supervision of the peer education .

Some of the peer educators are having good communication skills, But the  knowledge about STI / RTI, need to be strengthened. condom demonstration skills are good. The interactions with the community members are also supporting this observation. Lack of proper training and monitoring mechanism is lacking. The concept of BCC to be imparted to the peer educators so as to deliver quality services. The  supportive supervision required.

8. Supervision- mechanism, process, follow-up in action taken etc

The project conducts weekly review meetings were all the staffs & PE attending and discussed more over the dues for availing the services. Based upon that plan is reviewed. Monthly meeting conducted in every month. The PD’s presence and inputs observed .

IV. Services

- Availability and quality of STI services and documentation:

| Place | Footfall | Remark |
| --- | --- | --- |
| Transport Nagar , Dimna | 7562 | 3 days a week |
| Transport Park Burmamines | 9257 | 3 days a week |
| JMD , Jugsulai | 345 | one day on second half of Friday |
| Total | 17164 |  |

As per the NACO /JSACS guidelines the registers maintained. Medicine stock register , referral slips , STI registers , referral registers, PPP Clinic Register & File, Counseling Register, ICTC Referral Register , ICTC Testing Register , ICTC Referral Slip, Govt. STD Clinic Referral Slip, PLHIV REGISER, STD Drug Stock Register, STD CMIS Report

2.Counsllor is having regular contact with the ICTC/DOTS center.

3.  Availability of Condoms-  only free condom distributed

Condom distribution is mainly through the peer educators.

The distribution mode of condoms is Free distribution.

The project demonstrate the condom demo and redemo with the HRG’s It reflects that the skill for usage of condoms provided and during the filed level FGD is confirmed with truckers group.

V. Community participation

1.  Collectivization activities: only 01 CBO formation under process since inception, perspectives of these groups towards the project activities.

2.  Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- Collectivization activities:

They have only one CBO formation under process.

Linkages

At present the project is having good linkages with the various service providers But there is no ICTC at Hospital.

| Month | ICTC Refer | ICTC Test | Reactive |
| --- | --- | --- | --- |
| April | 356 | 158 | 0 |
| May | 350 | 164 | 1 |
| Jun | 318 | 160 | 0 |
| July | 284 | 121 | 0 |
| Aug | 190 | 124 | 1 |
| Sep | 258 | 108 | 2 |
| Oct | 175 | 108 | 2 |
| Nov | 269 | 109 | 0 |
| Dec | 304 | 122 | 3 |
| Jan | 219 | 69 | 0 |
| Feb | 265 | 172 | 0 |
| Mar | 276 | 159 | 0 |

Support system developed with various stakeholders and involvement of various stakeholders in the

| Organisation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Customer Services Division, Tata Steel |  |  |  | S S Ali | Sr Manager | 9234000829 |
| Sai Baba Transport |  |  |  | Sri Govindji | President | 9204065430 |
| Siddhi Binayak |  |  |  |  |  |  |
| Tata Motors |  |  |  | Ms Saileja |  | 9973563314 |
| Awadh Dental College |  |  |  | Mr Sanad |  | 9122584941 |
| Andra Karnataka |  |  |  | Md Rafiq | Treasurer | 9771587688 |