Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

| Background of Project and Organisation: | Village Beneficiaries Education and Development Society (VBEDS) a nongovernmental and non profit organization established in the year 1990 . The organization was formed by the initiative of the founder Mrs. Buvaneswary with her vast experience in the field of social work by bringing the group of likeminded women together to serve the poor, marginalized and the needy in the society, without any caste, colour, creed and religious discrimination to give meaning to human life and its values, to serve the un served |
| --- | --- |
| Name and address of the Organization: | Village Beneficiaries Education and Development Society (VBEDS), 92, Yathawal Street, Poovam, Varichikudy (PO), Karaikal – 609 609 |
| Chief Functionary: | V. Buvaneswary, Secretary Cum Project Director |
| Year of establishment: | 1990 |
| Year and month of project initiation: | 2007 |
| Evaluation team : | External Evaluators 1.Maria Benno 2.Vijay Anand 3.V. Raghuram, Vedam & Co SACS/TSU representative 1.Balamurugan, AD- M&E PACS |
| Time frame: | 4th to 6th February 2016 |

Profile of TI

(Information to be captured)

| Target Population Profile: FSW / MSM / IDU / TG/TRUCKERS / MIGRANTS | FSW/MSM |
| --- | --- |
| Type of Project: Core/ Core Composite / Bridge population | Core Composite |
| Size of Target Group(s) | FSW : Target=442 Registered= 595 Drop Out=164 New ID=8 Ongoing=431 MSM: Target- 458 Registered=604 Drop Out=169 New ID=18 Ongoing = 435 |
| Sub-Groups and their Size | FSW- Street based=132 Home based=57 Lodge based=25 Brothel based=18 MSM- Kothi=357 Double Decker=72 Transgender=6 |
| Target Area | Thirunallar, T.R. Pattinam, Neravy, Kottucherry, Karaikal Commune, Nedungadu |

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme Interaction with key office bearers, 2-3, of the implementing NGO/CBO to see their vision about the project, support to the community, initiation of advocacy activities, monitoring the project etc…

Interaction with key office bearers namely Treasurer, Secretary and Member reveal that two programmes namely SHG and TI is implemented by VBEDS. The Secretary’s direct involvement is observed in the TI than the other office bearers. It was shared that they do have update on the project activities from time to time. The Secretary is the Project Director and directly involves in addressing advocacy activities and monitors the project. In the last one year her involvement or engagement in the TI has been very less on account of certain domestic reasons

II. Organizational Capacity

1. Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover

- 86% staff turnover witnessed, with 6 ORWs resigning, M&E and Accountant position merged one staff terminated - It is observed that for 3 resigned ORWs 5-8 days of salary not given and R. Rajkumar was paid salary for April 2015 where there is no appointment order for this period at the time of evaluation - In the last one year Project Director’s involvement or engagement in the TI has been very less on account of certain domestic reasons while other office bearers involvement or monitoring not observed - ORWs for the MSM component are from the community - Though documents are updated, quality of documentation is not verifiable as presence of HRGs in the field not observed - It appears that most of the data are machine generated and translated to the base documents while it has to be vice versa - Programme Manager lacks supervisory and monitoring skills

2. Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

M&E has undergone two trainings, however no reports available to this effect. PE have been oriented and related reports available and verifiable

3. Infrastructure of the organization

Infrastructure of the organization is adequate. Name board is a new Flex board

4. Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

- Though documents are updated, quality of documentation is not verifiable as presence of HRGs in the field not observed - It appears that most of the data are machine generated and translated to the base documents while it has to be vice versa - Form A for those HRGs identified in since 2007 on are not updated in the NACO format and available only in the USAID format at the time of evaluation - Mismatches observed in Staff movement register and their participation in hotspot meeting minutes in some cases and PM was on leave and his participation in the hotspot meeting recorded and signed by PM - Committees namely DIC level management committee, condom committee, STI committee, crisis management committee are only as records and same HRGs are members of most of the committees - Two events reported one in 2014 with 18% HRG participation and one in 2015. A health camp (voucher no. 214) followed by event (voucher no.213), no proper supportive documentation to this effect – health camp – doctors’ treatment register not available, HRG participation/ registration available without details of the programme/event, however expenses have been booked both for health camp and event during the assessment period

III. Program Deliverables

Outreach

| Indicators | Observations |
| --- | --- |
| 1. Line listing of the HRG by category | Master register updated till 5th December 2015, line list available by category |
| 2. Registration of migrants from 3 service sources i.e. STI clinics, DIC and Counseling. | FSW : Target=442 Registered= 595 Drop Out=164 New ID=8 Ongoing=431 MSM: Target- 458 Registered=604 Drop Out=169 New ID=18 Ongoing = 435 |
| 3. Registration of truckers from 2 service sources i.e. STI clinics and counseling. | NA |
| 4. Micro planning in place and the same is reflected in Quality and documentation. | updated hotspot analysis and micro plan available for all hotspots. ATP available as document the same being used by ORW to track in delivering project services not observed however individual HRGs are tracked for RMC, ICTC, Syphilis testing with the computerised individual tracking sheet. Verifiable from referral slips and registers, it is observed that in some referral slips corrections are made w.r.t name and date |
| 5. Coverage of target population (sub-group wise): Target / regular contacts only in HRGs | FSW: Target = 442 / Regular contact is 363 (Average of last three months) 84% MSM: Target = 458 / Regular contact is 379 (Average of last three months) 87% |
| 6. Outreach planning – quality, documentation and reflection in implementation | Outreach plan available and verifiable. Form B is maintained by the ORW, prioritization of HRG based on risk and vulnerability data not observed. Form A for those HRGs identified in since 2007 on are not updated in the NACO format and available only in the USAID format at the time of evaluation. Prioritization of HRG is not done by ORWs based on risk and vulnerability data. The project team lacks conceptual clarity on the TI programme, in reporting of the actual data for the services uptake, in rendering quality outreach messages, and also do risk - vulnerability assessment along with condom demand on quarterly basis. |
| 7. PE: HRG ratio, PE:migrants/truckers | FSW 1:54 ; MSM 1:62 Observed |
| 8. Regular contacts ( as contacting the community members by the outreach workers / Peers at least twice a month and providing services such as condoms and other referral services for FSW and MSM, TG and 20 days in a month and providing Needle and Syringes) - understanding among the project staff, reflection in impact among the community members | FSW= 363 & MSM= 379 regular contact, though reported and documented HRG visibility very poor both among FSWs & MSMs during field visit at the time of evaluation |
| 9. Documentation of the peer education | Form B is maintained by ORWs, Except for a few PE others lack knowledge about Form B. Prioritization of HRG is not done by ORWs based on risk and vulnerability data. |
| 10. Quality of peer education- messages, skills and reflection in the community | As inferred from the FGD with the PEs , they go to the field two days in a week and meet the HRGs. Their knowledge on project services and the condom demonstration skill is poor. FSW representation of PEs were low for the FGD. |
| 11. Supervision- mechanism, process, follow-up in action taken etc | - It is observed that ATP is available, and the Monitoring check list does not match with that of the movement register is some cases. No PE were present during field visits, during group discussion with PEs it was inferred that 4 days of field visits are made by PEs. - Monitoring and supervision on the part of the programme manager minimal - Project Director’s active involvement in the TI in the assessment period not very visible on account of domestic issues |

IV. Services

1. Availability of STI services – mode of delivery, adequacy to the needs of the community.

Referrals for STI services are made to Government Hospital Karaikal, designated STI clinic and services are adequate

2. Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

Government facilities follow NACO guidelines. Stock out of NACO supplied STI kits, however the kits are purchased and issued to the

3. In case of migrants and truckers the STI drugs are to be purchased by the target population, whether there is a system of procurement and availability of quality drugs with use of revolving funds.

NA

4. Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centres.

Syndromic case management treatment protocol adhered at Govt. STI clinic, though there had been shortage of NACO STI kits they procure and provide to all walkin clients

5. Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

- As the TI has no clinic, there is no scope for stock register for medicines and treatment registers. At the government facility treatment register and patient cards available - STI /ICTC/ RMC register maintained by the TI counsellor also capture PT - Referral slips available and verifiable , except in some cases for corrections in name and date

6. Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

- Condom distribution is through hand to hand, outlets and CSM - 190516 condom distributed. Hand to hand distribution =180749. Outlet=9767 Lubricants distributed 18802 - No stock out during assessment period - As per record sale is 658 pieces, the account for the cash through CSM not observed in the TI.

7. No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

- 190516 condoms distributed. Hand to hand distribution =180749. Outlet=9767 Lubricants distributed 18802 - As per record sale is 658 pieces, the account for the cash through CSM not observed in the TI - Gap of 3% observed Demand vs Supply

8. No. of Needles / Syringes distributed through outreach / DIC.

NA

9. Information on linkages for ICTC, DOT, ART, STI clinics.

Adequate linkages with ICTC, DOT, ART, STI clinics established. For ART referrals made to ART Center Nagapattinam. For ICTC: Government hospital Karaikal, Community Health Centre Thirunallar, Upgraded Primary Health Centre Nedungadu & Primary Health Centre Vizhithiyur

10. Referrals and follows up

- FSW= 244 (57%) Twice RMC against 431 ongoing & MSM= 326 (75%) Twice RMC against 435 ongoing. Verifiable from register and referral slips and visit made to the STI Department - As per MIS 6 out of 8 newly identified FSWs have undergone PT & 13 out of 18 newly identified MSMs have undergone PT. Verifiable from referral slips and register however not verifiable from interactions during field visits - It was shared and observed that all HRGs referred to ICTC are tested for Syphilis also. Referral slips verifiable, however register only reflects ICTC and not syphilis. HRG visibility during the field visit was very poor. 7% gap observed from referral vs tested among FSW & 2% gap observed from referral vs tested

V. Community participation

1. Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

Committees namely DIC level management committee, condom committee, STI committee, crisis management committee are only as records and same HRGs are members of most of the committees 2-3 meetings were organized in the assessment period. No ORWs representation documented. PEs and HRGs are not aware that such committees function Initiative in forming a CBO by the TI not observed. From the FGD it is inferred that the MSM have a CBO of their own , this was not reflected during interactions in the field not desk review.

2. Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

Two events reported one in 2014 with 18% HRG participation and one in 2015. A health camp (voucher no. 214) followed by event (voucher no.213), no proper supportive documentation to this effect – health camp – doctors’ treatment register not available, HRG participation/ registration available without details of the programme/event, however expenses have been booked both for health camp and event during the assessment period The community participation in the project activities is only limited to only being beneficiaries of services. Apart from that they are not taking any active role in steering the project. Almost all the project committees are in the document level and have few HRGs rather than PE & ORWs as its members. As per record very few HRGs are part of the DIC committee

VI. Linkages

1. Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

Linkages with various service providers namely ICTC, STI, TB clinics adequate

2. Percentages of HRGs tested in ICTC and gap between referred and tested.

FSW =90% MSM=99% tested in ICTC. 7% gap observed from referral vs tested among FSW & 2% gap observed from referral vs tested.

3. Support system developed with various stakeholders and involvement of various stakeholders in the project.

One stakeholder meeting held on11.08.2014 and met with ICTC counsellor and STI counsellor, meeting with other stakeholders not organized at the time of evaluation. One stakeholder participated in addressing the issues relating to project services

Performance

| Indicator | Target | Achievement | Percentage (%) |
| --- | --- | --- | --- |
| Coverage | 900 | 866 | 96% |
| Unique contact | 900 | 797 | 89% |
| Regular contact | 726 | 742 (Average of last three months) | 102% |
| STI clinic attendance | 3600 | 1717 | 48% |
| ICTC testing | 1800 | 1327 | 74% |
| Syphilis Screening | 1800 | 1327 | 74% |
| Condom demand / Supply | 196153 | 190516 | 3% |
| Number of PLHA/ linked to ART | 1 | Linked to ART | 100% |

VII. Financial systems and procedures

1. Systems of planning: Existence and adherence to NGO-CBO guidelines/ any approved systems endorsed by SACS/NACO- supporting official communication.

The NGO has not produced agreement, if any, entered with PSACS. The only evidence for the programme is a photocopy of budget communication. We are advised by the NGO that extant norms are followed. We have also not come across any instance of deviation during the evaluation.

2. Systems of payments- Existence and adherence of payments endorsed by SACS/NACO, availability and practice of using printed and serialized vouchers, approval systems and norms, verification of documents with minutes, quotations, bills, vouchers, stock and issue registers, practice of settling of advances before making further payments.

A proper system for payment is in vogue. Vouchers are prepared and expenses incurred against vouchers prepared. Vouchers carry signatures of the Accountant as preparer, Project Manager as Checker and Project Head as the approving functionary. Printed and serialized voucher forms are in use and it is generated in Tally programme. Accounting records and programme records should carry their respective references but this is not being done. System of giving advance for expenses, if any in vogue, is not evident.

3. Systems of procurement- Existence and adherence of systems and mechanism of procurement as endorsed by SACS/NACO, adherence of WHO-GMP practices for procurement of medicines, systems of quality checking.

Competitive quotations have not been obtained for purchase of lubricants.

4. Systems of documentation- Availability of bank accounts(maintained jointly, reconciliation made monthly basis), audit reports

NGO’s Secretary and Treasurer are the joint signatories who operate the Savings Bank exclusively maintained for the project with India Bank, Karaikal Branch. Bank reconciliation statements are prepared every month. Audit reports are being attended to.

VIII. Competency of the project staff

VIII a. Project Manager Educational qualification & Experience as per norm, knowledge about the proposal, Quarterly and monthly plan in place, financial management, computerization and management of data, knowledge about program performance indicators, conduct review meetings and action taken based on the minutes, mentoring and field visit & advocacy initiatives etc.

Programme Manager is qualified with Masters in Social Work, and 3 years experience, however lacks clarity on the TI concept , follow up on the previous evaluation recommendation not available with the PM and not followed. Lacks monitoring and supervisory skills, not ensuring quality in documentation especially hotspot meetings, committee meetings and events, with manipulation of information, reporting those meetings not attended or conducted as being attended or conducted. Furnishing old participants list pertaining to fertility screening for the current events, no details of the programme nor venue date mentioned, a pathetic scenario

VIII b. ANM/Counselor Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers, field visits and initiation of linkages etc

Counsellor is also a post graduate in Social Work and about three and half year experience with the TI. Has knowledge of counselling and HIV, symptoms of STI, maintenance and updating of data and registers, home visits made to HIV positive HRGs and ensure followup

VIII c. ANM/Counselor in IDU TI Clarity on risk assessment and risk reduction, knowledge on basic counseling and HIV, symptoms of STIs, maintenance and updating of data and registers. Working knowledge about local drug abuse scenario, drug-related counseling techniques (MET, RP, etc.), drug-related laws and drug abuse treatments. For ANM, adequate abscess management skills.

NA

VIII d. ORW Knowledge about target on various indicators for their PEs, outreach plan, hotspot analysis, STI symptoms, importance of RMC and ICTC testing, support to PEs, field level action based on review meetings etc..

One MSM ORW seems to be familiar with both MSM & FSW field, who was part of the field visits planned for the evaluation team. The newly recruited FSW ORW gain knowledge on target, various indicators for the PEs, out reach plan, hotspot analysis etc. Though documentation seem to be available HRG presence not observed at the time of evaluation One new ORW appointed for FSW intervention before two months has more targets than the ORW

VIII e. Peer educators Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc.

Sanctioned is 15 PEs and 13 PEs were present for FGD. Prioritization of hotspots, importance of RMC and ICTC testing, condom demonstration skill, knowledge about condom depot, symptoms of STI, knowledge about service facilities etc. not adequate. They don’t maintain records such as daily dairy, FORM-B and outreach plan. They shared that they go to the field two days in a week to meet the HRGs. In general they cover one third of sanctioned HRGs. Their knowledge on project services and the condom demonstration skill is poor

VIII f. Peer educators in IDU TI Prioritization of hotspots, condom demonstration, importance of RMC and ICTC testing, knowledge about condom depot, symptoms of STI, working knowledge about abscess management, local drug abuse scenario, de-addiction facilities etc.

NA

VIII g. Peer Educators in Migrant Projects Whether the Peers represent the source States from where maximum migrants of the area belong to, whether they are able to prioritize the networks/locations where migrants work/reside/access high risk activities, whether the peers are able demonstrate condoms, able to plan their outreach, able to manage the DICs/ health camps, working knowledge about symptoms of STI, issues related to treatment of TB, services in ICTC & ART.

NA

VIII h. Peer Educators in Truckers Project Whether the peers represent ex-truckers, active truckers, representing other important stake holders, the knowledge about STI, HIV, and ART. Condom demonstration skills, able to plan their outreach along with mid-media activity, STI clinics.

NA

VIII i. M&E officer Whether the M&E officer ( FSW and MSM/TG TIs with more than 800 population and all migrant TIs are eligible for separate M&E officer) is able to provide analytical information about the gaps in outreach, service uptake to the project staff. Whether able to provide key information about various indicators reported in TI and STI CMIS reports.

M&E Cum Accountant though qualified with masters in commerce lacks knowledge on accounting principles. Lacks ability in providing analytical information on gaps in outreach, service uptake and in providing key information about various indicators. Work report of the M&E does not match with the movement register and the minutes of the hotspot meetings on verification

IX. a. Outreach activity in Core TI project Interact with all PEs (FSW, MSM and IDU), interact with all ORWs. Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

It is observed from the interaction with the ORWs that quarterly hotspot analysis is done and documented. Outreach activities reflect uptake of services, however in few cases gaps seen. ATP available and due list to track HRGs for service uptake. CSD not done in the year 2015 There is gap in the reported coverage of HRGs and actual visibility of the HRGs in the field. Though the TI project reports to be having an ongoing of 886 HRG population, only 11 HRGs (FSW&MSM) were met by the evaluation team in two days. The team gives priority for the service uptake and they visit different ICTC, STI centres and have good rapport with them. ORWs prepare weekly plan and monitor the activities of the PEs in the field.

IX. b. Outreach activity in Truckers and Migrant Project Interact with all PEs and ORWs to understand whether the number of outreach sessions conducted by the team is reflecting in service uptake that is whether enough clinic footfalls, Counseling is happening. Whether the stake holders are aware of the outreach sessions. Whether the timings of the outreach sessions are convenient / appropriate for the truckers/migrants when they can be approached etc.

NA

X. Services Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

As per the reported data and documentation the service uptake appears to be satisfactory, however poor visibility of HRG observed in the field at the time of evaluation

XI. Community involvement How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

Except for the two community staff (MSM ORWs) community participation not observed, Programme management committee not formed or functioning in the assessment period. Also in the other committees of the TI it is observed that only 5-6 HRGs are mentioned as members and the same are members of almost all the committees, however HRGs not aware about these committees as inferred from field interactions

XII. Commodities Hotspot / project level planning for condoms, needles and syringes. Method of demand calculation, Female condom programme if any,

Condom demand analysis is done quarterly, however it is observed that there is gap of 3%

XIII. Enabling environment Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

Three advocacy meetings have been recorded, however interactions or visits to meet the relevant stakeholders not organized during evaluation, plan for advocacy not observed

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes, social entitlements etc.

It was shared by the staff team that they had facilitated HRGs in accessing social protection schemes, however there was no supporting documents to this effect

XV. Best Practices if any

NA

Annexure C

Confidential                                  Reporting form C

EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Maria Benno | 9444066739 |
| Vijay Anand | 9944466857 |
| Raghuram. V Vedam & Co | 8489008370 |
| Officials from SACS (as observers) Balamurugan | 9443623973 |

| Name of the NGO: | Village Beneficiaries Education and Development Society (VBEDS) |
| --- | --- |
| Typology of the target population: | Core Composite |
| Total population being covered against target: | FSW : Target=442 Registered= 595 Drop Out=164 New ID=8 Ongoing=431 MSM: Target- 458 Registered=604 Drop Out=169 New ID=18 Ongoing = 435 |
| Dates of Visit: | 4th to 6th February 2016 |
| Place of Visit: | Karaikal Region |

Overall Rating:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| Below 40% | D | Poor | Recommended for |
| 41%-60% | C | Average | Recommended for continuation with closer monitoring from SACS |
| 61%-80% | B | Good | Recommended for continuation |
| >80% | A | Very Good | Recommended for continuation with specific focus for developing learning sites |

Specific Recommendations:

Organization Capacity: - Review the recruitment process and minimize staff turnover - Project Holder to be more actively involved and engaged in the effective implementation of the TI with increased percentage of time in programme monitoring - Revisit the recruitment of PE positions and minimize PE turnover - PM to be oriented on overall TI concept and capacity built on roles and responsibilities and supervisory skills - Ensure all formats and documents reflect the factual information and data reported to come from the outreach activities in the field - Community participation can be increased by identifying potential HRGs who can take leadership and involve in planning, implementation and monitoring of the TI project - Staff to have understanding of their roles & responsibilities, may be issued in the local language - M&E officer to have clarity in role and plan field visits to monitor and validate the data shared by the outreach team and counsellor Out Reach: - Validate the available line list, address those HRGs more at risk and vulnerable - Outreach tools to be effectively used in targeting those HRGs who are vulnerable and at risk - Staff review meetings not to limit to weekly reporting also to discuss field issues and other aspects pertaining to effective implementation of TI Clinic Services: - Outreach team to strengthen regular contact with those HRGs more at risk and vulnerable and increase RMC (only 66%) - Follow up all STI diagnosed clients ,ensure complete treatment, partner treatment and partner counselling - To ensure data correlation from HRG presence, referral slips to formats and registers - Field counselling to be increased for more familiarity among HRGs Commodities: - Strategically locate condom outlets in all hotspots - To have account for the sale of CSM and the cash inflow Enabling Environment: - TI project to have clarity on the functions of the various committees, ensure periodic meetings are conducted with increased HRG representation in the committee as members - TI project team to gather issues from HRGs through hotspot/DIC level meetings, plan and conduct advocacy meetings Recommendation to SACS: - Closer monitoring from SACS Recommendation to TSU - Closer handholding in strengthening the quality of documentation - As project staff lack understanding and clarity on the role of advocacy in the project. The project team to be helped by TSU to develop understanding and a strategy for advocacy

Name of the evaluators				Signature

| Maria Benno |  |
| --- | --- |
| Vijay Anand |  |
| Raghuram. V Vedam & Co. |  |