Annexure: B

Reporting Format-B

Structure of the Detailed Reporting format

(To be submitted by Evaluators to SACS for each TI evaluated with a copy to NACO)

Introduction

- Background of Project and Organization

Village Development Team – Non-Government Organization was registered under the Societies Registration Act 1860 in the year 2000.

The Organization is working in the field of Promotion of National Integration, Adventure Training Camp, Environmental science, TI Programme for Prevention and control of HIV/AIDS amongst Female Sex Worker, Women empowerment, Career Counseling programme for adolescents; PPTCT Project, IEC  and is also involved with several study/survey.

Village Development was initiated to Implementation the Targeted Intervention Programme for Prevention and Control of STI/HIV/AIDS amongst Female Sex Worker in the Agartala Municipality area in the year 2004. Then the project extended and also continuing the current financial year (2015-16) for SADAR Sub-division (West District), Sonamura and Bishalgarh Sub-division (Sepahijal District).

- Name and address of the Organization

Village Development Team

Hospital Extension Road, Gandhighat,

Agartala-799 001, Tripura West

Email- vdteam@rediffmail.com, vdteam.tripura@gmail.com

Contact No: +91 9436126512

- Chief Functionary:  Mrs. Bharati Chakrobarty (Secretary)

- Year of establishment:  16th March 2000

- Year and month of project initiation:

Project is running from May 2004

- Evaluation team

Mr. Tushar Kanti Dey (Team Leader)

Mr.Debajit Gupta (Co evaluator)

Mr. Ashim Mukherjee (Finance evaluator)

- Time frame

10th to 12th December 2015

Profile of TI

- Target Population Profile: FSW

- Type of Project:  Core

- Size of Target Group(s) -604 FSW (active population)

- Sub-Groups and their Size

FSW

Home based	:	479

Highway based	:	  58

Hotel based	:	  44

Street based	:	  23

- Target Area

- Tulsibari

- Melagharh

- Box- Nagar

- Agartala Sadar

- Sepaijola

Key Findings and recommendations on Various Project Components

I. Organizational support to the programme

- The organization support to the programme is moderate and the secretary is the sole office bearer concerned with project activities.

- The chief office bearers and the general members have no role in implementation of the programme and addressing crisis issues.

- The key office bearers were represented by the Secretary of the organization.

- It was found that the secretary mark her presence in the review meetings conducted as all review meeting bear her stamp and signature.

- During the time of visit the team got to meet only one of the GB members so the opinion and philosophy of other members about the organization and the project could not be understood.

II. Organizational Capacity

- Human resources: Staffing pattern, laid down reporting and supervision structure and adherence, role and commitment to the project, perspective of the office bearers towards the community at a large staff turnover

TI Project staff patterns		:

Project Director			:	01

Project Manager		:	01

M & E Assistant cum Accountant:	01

Counselor			:	01

ORW				:	03

Peer				:	10

- Below is the staff list which reflects the name, designation and qualification of the individuals employed with the TI.

| Sl-No | Name | Designation | Education Qualification | Date of Joining |
| --- | --- | --- | --- | --- |
| 1 | Rupali Chakraborty | Project Manager | B A Passed, Diploma in Computer Application, Certificate course on Traning in First Aid. | 1st August 2008 |
| 2 | Dipanka Bhattacharjee | Counselor | BA in Sociology | 1st November 2013 |
| 3 | Pinku Datta | M & E Assistant cum Accountant | B. Com Certificate in Computer Application & Finacial Accounting | 1st April 2015 |
| 6 | Abhijit Das | ORW (FSW) | BA | 28th October 2015 |
| 7 | Manideepa Datta | ORW (FSW) | MRMD | 28th October 2015 |
| 8 | Runu Chandra Shil | ORW (FSW) | B.Com [Passed] | 1st November 2013 |
| 9 | Bharati Chakraborty | Project Director | MA in Mass Communication | 1st May 2004 |

- The organization has recruited all professionals and they have not promoted PEs or engaged community people in the project.

- The organization follows SACS – NACO norms for staffing pattern.

- Project team follows the reporting structure laid down by NACO- SACS and they maintain the documentations for the same.

- Documents for staff level supervision available but documents for management level supervision is not available with the project team.

- The organization has suffered a huge staff turnover but no effort seen to upgrade PE and promote them to ORW or upper level.

- Leadership is a big issue in the organization. The secretary is proactive and the Project manager burdening all responsibilities herself left smaller space for the rest of the team to grow.

- Capacity building: nature of training conducted, contents and quality of training materials used, documentation of training, impact assessment if any.

- Below is the given list of the trainings taken by the project staff:

| Sl-No | Date of Training | Details of Training | Training category | Organized by | Resource person | Participants |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | April 8, 2015 | Filling up B-Form, Due, Overdue, Logbook maintain, Condom demand analysis | Refresher | VDT | Counselor | Peer |
| 2 | June 16, 2014 | Field Approach, Form B, Condom Gap Analyses, ICTC and STI due-overdue | Refresher | VDT | Project Manager, TI | Peer |
| 3 | November 8, 2014 | Programme Management | Refresher and New Skill | VDT | Project Director, TI, VDT | Peer |
| 4 | November 28, 2014 | Field Counseling, HRG Counseling and Form-B | Refresher | VDT | Project Director, TI | Peer |
| 5 | January 27-28, 2015 | Programme Management | Refresher | TSACS | PD from different TI Project | Project Manager |
| 6 | January 29-30, 2015 | Clinic Management | Refresher | TSACS | Project Manager from different TI NGO and Programme Officer | Counselor |
| 7 | February 9-10, 2015 | Financial Management | Refresher | TSACS | AD, Finance, TSACS | Accountant |
| 8 | February 12, 2015 | Skill development, Typology of HRG, Services of HRG, Condom Gap Analysis | Refresher and New Skill | VDT | Project Director, TI, VDT | Peer |
| 9 | February 13-14, 2015 | TI Management | Refresher | TSACS | Regional Programme Manager | Project Director, TI |
| 10 | February 20-21, 2015 | Different Formats, Job responsibilities etc | Induction and Refresher | TSACS | ORW from different TI NGO | Peer |
| 11 | February 24-25, 2015 | Programme Management | Induction and Refresher | TSACS | Project Manager from different TI NGO | ORW |
| 12 | February 26-27, 2015 | Programme Management | Refresher | TSACS | PD from different TI Project | M & E Assistant cum Accountant |
| 13 | April 1-3, 2015 | Programme and Finance Management | Induction | VDT | PD and PM of NGO | M & E Assistant cum Accountant |
| 14 | April 20, 2015 | Programme and Finance Management | Induction and New Skill | VDT | Programme Officer, NERO | M & E Assistant cum Accountant |
| 15 | June 23. 2015 | Risk and Vulnerability - Skill development and field approach | Refresher | VDT | Project Manager and Project Director | Peer |
| 16 | September 8, 2015 | Form - B, Due - Over due, Condom demand analysis | Refresher | VDT | Project Director | Peer |
| 17 | October 28-31, 2015 | Programme Management, Clinic Management, Concept of NACP, 17 Formats | Induction and New Skill | VDT | Programme Officer, NERO and PD | ORW |
| 18 | November 3, 2015 | Form - B, Due - Over due, TI Programme, Job responsibilities, Risk and Vulnerability | New Skill and Refresher | VDT | Project Director | Peer |

- Staff capacity has been built by TSACS and the organization.

- Staffs (Counselor, ORW and PEs) got refresher training.

- Induction training given to staffs though a new ORW joined a month back has yet to be inducted in the program.

- The TI has conducted in house training and it was found that the Project Director and NERO personnel facilitated trainings.

- Basic level understanding seems to be good among the PEs.

- Thematic trainings are suggested for both staff and PEs to name a few would be: sex and sexuality, technical documentation, micro planning, Advocacy from concept, planning to implementation.

- No training need assessment done by the TI and no impact assessment of the training has been done so far.

- Infrastructure of the organization

- The project office of the TI is in Agartala which is a rented building and it houses a DIC also.

- Office furniture and computer available in the project office requirement of the same has been fulfilled by the organization according to NACO – SACS norms/needs.

- The other DIC is having a very small room and it has got no enough space to make room for HRGs.

- Counselor room does not have adequate space for counseling, ensuring trust and confidentiality of the HRG.

- Documentation and Reporting: Mechanism and adherence to SACS protocols, availability of  documents, mechanism of review and action taken if any, timeliness of reporting and feedback mechanism, dissemination and sharing of the reports and documents for technical inputs if any.

- Team’s approach towards documentation is not encouraging and the evaluation team has found limitations in the area of documentation.

- The counseling register requires to be filled up properly.

- The ORWs require filling up Form A & D properly. ORWs have not found to record the mobility pattern and contact details of the HRG in Form A (HRG registration form). Form D (weekly activity details) has not been well understood by the ORWs and hence not furnished in detail.

- Form B is reflecting the risk assessment and vulnerability issues but the same requires periodical updation.

- Review meetings are conducted to discuss the achievement of the targets set in indicators. But the documentation and reporting system has not been monitored.

- Few PEs are known to be illiterate so the organization should develop pictorial outreach and micro-plans for their convenience.

- Many concepts of project documentation still not clear with the team.

- ORW level planning exists but at a very basic and nascent stage.

- It seems that the social maps are all drawn by the ORWs and the same has not been shared with the PEs as they found it difficult to find out hotspots and service facilities out of those maps.

III. Program Deliverables

Outreach

- Line listing of the HRG by category.

- A total of 604 individuals have been line listed by the project staff. This includes 604 FSW (Home based-479,  Highway based-  58, Hotel based-44, Street based-23)

- The project requires revalidation of the HRGs as the HRGs met during the visit do not believe that there are any FSWs at all in the area.

- It was evident that there are FSWs in that area but they were yet to be registered and line listed by the TI.

- Micro planning in place and the same is reflected in Quality and documentation.

- Micro planning in place but followed unevenly by the project staff and the PEs.

- The TI has done hot spot analysis of each and every hotspot to strategize outreach activity.

- The project staff has their plans in place, but ORWs are the ones who follow micro planning.

- Micro-planning in place and it reflects in quality and documentation but the same require improvement and to be reviewed after a given period after mapping the vulnerability of HRGs.

- In some places the team has found that form A has not been filled completely.

- Coverage of target population (sub-group wise): Target / regular contacts only in HRGs

- A total of 604 individuals have been line listed by the project staff. This includes 604 FSW (Home based-479,  Highway based-  58, Hotel based-44, Street based-23)

- 604 active FSW’s are covered by the Project staff.

- As per the records made available, regular contacts (twice in a month) are 576  FSW’s and once in a month with 589 FSWs.

- Outreach planning – quality, documentation and reflection in implementation

- Outreach planning done on a very basic level.

- ORWs put their efforts in documentation which is fairly visible but some gaps as mentioned above do exist.

- The understanding towards documentation is very poor among the personnel.

- The ORWs has got poor understanding of Form D and it has not been filled properly.

- The ORW has got a casual approach in feeling Form A and they had left some information to be filled.

- Form A does not bear movement status of the HRGs and they have not recorded the contact number of any individual HRGs.

- PE: HRG ratio, PE: migrants/truckers

- PE; HRG ratio 1:60 is fairly maintained.

- But the distribution of HRGs under each PE is uneven.

- Regular contacts ( as contacting the community members by the outreach workers / Peers at least visit the HRG twice a month and are providing services such as condoms and other referral services for FSW – Understanding among the project staff has got its reflection in impact among the community members

- The staff has a poor understanding of regular contacts, registered contacts and reached contacts at ORW level.

- It has been understood that the staff meet the HRG every fortnight and avail them required number of condoms and refer them to services and follow up if they are due to any services.

- The PEs meet HRGs twice a week and ORWs contact at least once in a week.

- Community of HRG is been provided condom in these visits and are referred for HIV and RPR tests if necessary and as per the schedule.

- ORWs and PE track individual HRG for service provisioning and refer them when they are due or overdue.

- Documentation of the peer education

- PEs are either semi literate or illiterate.

- PEs do not have basic understanding about the documentation.

- The PEs mostly remember the numbers of commodity distributed and name of the HRGs met which is shared to their respective ORW in charge and thus the team is skeptical about the quality of the document collected.

- ORWs help PEs to complete their documentation.

- Quality of peer education- messages, skills and reflection in the community

- PEs are very vocal and clear when they communicate though a few PEs are timid and require more capacity.

- Few PEs have got a good knowledge and their involvement in the project is remarkable.

- The PEs are a group of illiterate or semi literate people who require ORWs help to do the documentation.

- Most of the community members are satisfied by the services provided by the PEs.

- Most of the PEs are above the age group of 30.

- Supervision- mechanism, process, follow-up in action taken etc

- Supervision is done at two levels first at ORW level and second at PO level.

- The PD makes few field visits and approves bills and signs in required documents thus the evaluation team is skeptical about his role in monitoring and supervision.

- Proper documentation for this process is not followed by the project.

- No minutes available with the project staff for looking into follow up action taken by the management for any specific task assigned.

IV. Services

- Availability of STI services – mode of delivery, adequacy to the needs of the community.

- STI service is delivered through linkages with Govt. hospital examination.

- RMCs were done regularly with the HRGs.

- It was understood that all RMC’s are done by the PPP.

- Quality of the services- infrastructure (clinic, equipment etc.), location of the clinic, availability of STI drugs and maintenance of privacy etc.

- The STI services are provided through PPP and the clinic of which is assessable by the community.

- STI drugs were made available to the community.

- It was learnt from the HRG that privacy is not compromised in the outreach clinic.

- It was learnt that the medicine stock is distributed by the TI as prescribed from PPP’s clinic.

- No PPP doctor or clinic found to be in service during the time of visit so the quality cannot be assessed.

- Quality of treatment in the service provisioning- adherence to syndromic treatment protocol, follow up mechanism and adherence, referrals to VCTC,ART, DOTS centre and Community care centers.

- RMCs are evidently been done regularly.

- There are referrals to ICTC and STD clinic in Govt. set up for RPR and HIV testing and the project refer to the ICTC as well. And they have referred all HIV positive clients to the ART centre and adherence was evident while visiting the ART center.

- Medicines are distributed from clinic and stock register for the same maintained.

- Documentation- Availability of treatment registers, referral slips, follow up cards (as applicable- mentioned in the proposal), stock register for medicines, documents reflecting presence of system for procurement of medicines as endorsed by NACO/SACS and the supporting official documents in this regard.

- Documents and record keeping is a real issue with the TI and the necessary documents has not been maintained properly.

- Documents are maintained as per NACO- SACS guidelines, lack of understanding for the same is found with the project staff.

- Referral slips are found to be properly filled up.

- Follow up cards not found.

- Central stock registers are maintained.

- All CIF forms, Drug stock register were available at the NGO office.

- Availability of Condoms- Type of distribution channel, accessibility, adequacy etc.

No. of condoms distributed- No. of condoms distributed through different channels/regular contacts.

- No condom depots or linkages are established by the project staff.

- Condoms are distributed through PEs and ORWs.

- There are no condom outlets.

- During the project period from Dec 14 to Nov 15 the staff and the PEs have distributed 104149 condoms in the community against the demand of 107318 condoms.

- The project has marketed 10% of the condom demand through CSM.

- Female condom is not there in the project.

- Information on linkages for ICTC, DOT, ART, STI clinics.

- Project has good linkages with the existing govt. infrastructure for STI and allied services.

- A good rapport with the local govt hospital and its STI centre, DOT and ART centers has been maintained.

- Referrals and follows up

- As the project has strong linkages with the govt. health systems, referrals have not been a real issue with this project.

- Lack of Conceptual clarity within the field team and uneven planning may have a direct impact on the follow up part of the STI care component of the project, but follow-up of clients for the service is evidently good.

V. Community participation

- Collectivization activities: No. of SHGs/Community groups/CBOs formed since inception, perspectives of these groups towards the project activities.

- No SHGs have been formed.

- There is no initiation from the TI in formation of CBO.

- Community participation in project activities- level and extent of participation, reflection of the same in the activities and documents

- Community participation is until the level of PE only.

- Community involvement in the TI is limited to services and events organized.

- No project personnel are from the community and they have different committees where there is very little participation of the community.

- Documents reflect the participation of the community members in events organized by the project team.

- It was understood that the HRGs avail the DIC service.

VI. Linkages

- Assess the linkages established with the various services providers like STI, ICTC, TB clinics etc…

- The project team has good links with ICTC and consistently has been referring HRGs .

- It was found in the ICTC that group of HRGs together are brought in the facility.

- Percentages of HRGs tested in ICTC and gap between referred and tested.

- Almost 95% of the line listed HRGs have tested for HIV.

- Almost all referrals are accompanied so no gap between number of referred and number actually tested.

- Support system developed with various stakeholders and involvement of various stakeholders in the project.

- They have got strong linkages with ICTC, ART and STI clinic. The HRGs referred to the service providers are dealt in priority.

VII. Financial systems and procedures

- Systems of planning:  In our observation it is found that the existence system of “Village Development Team” is adherence to NGO guidelines and the approved system is also endorsed by SACS/NACO supporting official communication.

- Systems of payments- It is found that the existence system of payments is endorsed by SACS and NACO supporting officials. It may be pointed out that they are using printed vouchers having machine number and the ledgers are maintaining as per norms but it needs to develop and update. In our observation it is found that the ledger and account of “Social Marketing Fund”, “Loan Account”, “Salary Account” etc. are maintained as per NACO guidelines. Similarly “Fixed Assets” Ledger is maintained as per norms.

In our observation it is found that due to crisis of fund the management takes the loan from individual members through Bank Transfer for reimbursement of regular expenses and returns the loan through Bank when fund comes from TSACS.  Loan Register is maintained as per norms.

- Systems of procurement- In our observation it is found that the existence system of procurement is in adherence of policy of procurement as endorsed by SACS/NACO and also adherence of WHO-GMP practices for procurement of medicines and the systems of quality checking is require to develop.

- Systems of documentation- As per their NGO guidelines it is observed that they are maintaining separate Bank Account having two authorized signatories and the reconciliation is prepared as per the guidelines, but regarding authorized signatories we have not found any original documents at the NGO Office in our visit.

VIII. Competency of the project staff

VIII a. Project officer

Mrs. Rupali Chakrobarty        Educational Qualification: BA

Experience- She has been working in the TI since the inception.

- She has got very good understanding on the indicators of the TI components.

- She is good in field work but technical knowledge requires development.

- Technical inputs recommended are: computerization and management of data, knowledge about program performance indicators, mentoring and field visit & advocacy initiatives etc.

- She requires monitoring the project activity and analyze data and authenticate the validity of the same.

- She herself is a state resource and hence her capacity of project management is understandably high.

VIII b. ANM/Counselor

Mrs. Dipanka Chattarjee,                             Educational qualification- BA (Sociology)

Experience- He has been working in the TI for the last 7 year of which the last 2 year as an ANM/counselor.

- He has got a very poor understanding about the basics of counseling.

- His understanding about the basics of HIV/AIDs and STI is clear though.

- The counselor helps the PO in data analysis.

- The counselor is not very popular among the stakeholders.

VIII d. ORW

Mrs. Abhijit Das,                                Educational Qualification: BA

Mr. Manideepa Datta,                      Educational Qualification: MRMD

Mrs. Runu Chandra Shil,                   Educational Qualification: BCom

- No ORWs are from the community.

- Most of them are young in the TI and they have not been provided with proper induction.

- The ORWs clarity about risk assessment requires enhancement.

- They have very poor knowledge on various targets, outreach plan, STI symptoms, importance of RMC and ICTC testing.

- They share a good rapport with their PEs.

- ORWs are aware and confident about field level situation which is a great sign.

VIII e. Peer educators

- They have knowledge on importance of RMC and ICTC testing.

- Excellent communication skills among the PEs though few PEs are timid.

- Demonstration skills require improvement.

- Knowledge on symptoms of STI, knowledge about service facilities etc is good.

- The PEs are quite involved in the project and the TI require to ensure greater involvement of the PEs in the intervention.

IX. a. Outreach activity in Core TI project

Interact with all PEs (FSW, MSM and IDU), interact with all ORWs.  Outreach activities should reflect in the service uptake. Evidence based outreach plan, outreach monitoring, hotspot wise micro plan and its clarity to staff and PEs etc.

- The PEs and ORWs conduct regular session with the HRGs and it is evident that the population is indeed going to the facilities.

- Service uptake is yet to be spontaneous and most of them are referred to the facilities being accompanied to avail the services.

- Most of the hotspots are dispersed so outreach is not possible at every point of time. They need to plan outreach keeping in lieu the distance and availability issues.

- Outreach monitoring need to be more frequent.

X. Services

Overall service uptake in the project, quality of services and service delivery, satisfactory level of HRGs,

- Overall the community seems to be satisfied by the services provided by the project team.

- The TI got a good referral and linkages system with Govt. STI clinic and all referred for ICTC do visit STI clinic during their time of visit in ICTC.

XI. Community involvement

How the TI has positioned the community participation in the TI, role of community in planning, implementation, Advocacy, monitoring etc

- Community involvement limited to service provision and community events at project level only.

- Much work needs to be channelized on crisis management and advocacy efforts.

XII. Commodities

Hotspot / project level planning for condoms, needles and syringes.  Method of demand calculation, Female condom programme if any,

- ORWs plan condom gap analysis which is a good sign.

- The team has a system for demand calculation, which now needs to be percolated towards PEs.

- The TI has got CSM in place but it has distributed only 10% of the required condom through CSM.

- No female condom programmes in place.

XIII. Enabling environment

Systematic plan for advocacy, involvement of community in the advocacy, clarity on advocacy , networks and linkages, community response of project level advocacy and linkages with other services etc. In case of migrants (project management committee) and truckers (local advisory committee) are formed and they are aware of their role, whether they are engaging in the programme.

- Conceptual clarity for advocacy component needs to be imbibed in the project team as well as organizational management.

- No plan for advocacy in place.

- Crisis committee in place but participation of different stakeholder in the same is not ensured.

- Linkages and networking with the Govt. facilities and other organizations are evidently there but the same require enhancement as there is a great mismatch of figures collected from sources and that of the TI.

XIV. Social protection schemes / innovation at project level HRG availed welfare schemes,  	social 	entitlements etc.

- The organization has formed no SHG groups and has not initiated the process of CBO formation.

- There is no effort from the organization to avail the HRGs with welfare schemes or social entitlements.

XV. Best Practices if any

- No innovations or best practices in place with the project.

Annexure C

Confidential                                                                                                                      Reporting form C	        EXECUTIVE SUMMARY OF THE EVALUATION

(Submitted to SACS for each TI evaluated with a copy to NACO)

Profile of the evaluator(s):

| Name of the evaluators | Contact Details with phone no. |
| --- | --- |
| Mr. Tushar Kanti Dey (Team leader) | 9434738954 e-mail: tumakh@gmail.com |
| Mr. Debajit Gupta (co-evaluator) | 9401739988 e-mail: debajitgupta@yahoo.co.in |
| Mr. Ashim Mukherjee (Finance Evaluator) | 9433383101 e-mail: saiasim_mukherjee@rediffmail.com |

| Name of the NGO: | Village Development Team |
| --- | --- |
| Typology of the target population: | FSW |
| Total population being covered against target: | Target- 641( FSW) Covered- 604 ( FSW) |
| Dates of Visit: | 10th December to 12th December 2015 |
| Place of Visit: | Agartala, West Tripura |

Overall Rating based programme delivery score:

| Total Score Obtained (in %) | Category | Rating | Recommendations |
| --- | --- | --- | --- |
| 71.3% | B | Good | Recommended for continuation. |

Specific Recommendations:

- Staff capacity building should be developed at the earliest and induction of staff requires to be done. - Thematic trainings are suggested for both staff and PEs to name a few would be: technical documentation, Advocacy from concept, planning to implementation. - SHG groups to be formed and formation of CBO should be initiated. - It is imperative for the management of the organization to understand finer issues of the HRG groups and initiate their involvement in project work. - The TI requires revalidation of the HRGs and the core population to be included. - The PO and PM require enhancing knowledge on project planning and making use of available financial resources. - Inputs for documentation from conceptualization to its end use. - The TI should frame policies and avoid turnover. - TI requires upgrading and mentoring PEs to become ORWs. - The PD requires disseminating the power structure and giving space for others to show their trait of leadership which will make the team dynamic.

Name of the evaluators				Signature

| Mr. Tushar Kanti Dey (Team leader) |  |
| --- | --- |
| Mr. Debajit Gupta ( Co-Evaluator) |  |
| Mr. Ashim Mukherjee (Finance Evaluator) |  |